## Sheet1
Date | 2026-05-04
Notes | 1. Item ID = 7 Digits (Month + Date + Year) - date proposed
2 Status = N = New, A =Active, C = Completed I = Inactive
Line | Item ID | Status | Proposed by | Description | Responsibility | Status
1 |  | A | G. Schwartz | Install Speed Signs | M. LaCasse | Scheduled for April/May 2026
2 |  | A | M. LaCasse | Tree Removal at Route 12 and Greaves Hill Road | M. LaCasse | Joint Effort with the State of VT. Possible by the end of the month
3 |  | A | G. Schwartz | Estimate for ramp and stair replacement at Town Hall | T. Braun | Trevor contacting contractors and looking into possible grants
4 | 31126.1 | A | G. Schwartz | Town Appropriations | N. Davis | Nancy has begun reserch
5 | 31126.2 | A | N. Davis | Select Board SOP's | T. Braun | Original to be in Town office and reviewed once a year. Copy to be on website for reference
6 | 31126.3 | A | N. Davis | Emergency Plan to be put on Website | T. Braun | Plan to be created with help from LCPC. Fire house to be primary and new Town garage secondary location until emergency generator is installed.
7 | 31126.4 | A | M. LaCasse | Create Garage Demo RFP/Demolish existing garage | M. LaCasse | Work to begin after July 1 2026 Due to budget year
8 | 31126.5 | C | M. LaCasse | Create Lawn Mowing RFP | M. LaCasse | RFP created and bids due on May 1, 2026
9
10
11
12
13
14
15
16
17
18
19
20
21